## Executive Summary
MODEL ACTIVITY TRACKER — ANALYSIS REPORT ¦ Q1-2025 → Q1-2026
Reporting Period: Q1-2025 → Q1-2026 ¦ Prepared: May 2026 ¦ Classification: Confidential
TOTAL MODELS |  | COMPLETED ✓ |  | NO VALIDATION | WITH ISSUES | COMPLETION %
443 |  | 121 |  | 35 | 322
KEY FINDINGS AT A GLANCE
Severity | Indicator | Models | Finding / Description
CRITICAL | 🔴 | 35 | 35 models have had NO validation activity (FSV/AR/LSV) between Q1-2025 and Q1-2026. Require immediate triage to determine if retired, in scope, or missed.
HIGH | 🟠 | 61 | 61 models have an AR available but OGM Plan is missing despite the validation falling after the 07/01/2025 cutoff. OGM plan must be obtained or exception documented.
HIGH | 🟡 | 39 | 39 models are missing QC documentation post the 10/01/2025 cutoff. QC evidence must be located or validation re-performed.
INFORMATIONAL | 🟢 | 91 | 91 models are Retired / Re-Designated / Cancelled / Not in Use. Should be formally closed in the tracker and communicated to the client.
IMPORTANT NOTES
1. All counts are based on data visible in the tracker as of May 2026. Counts marked ~ are estimates from comments and should be confirmed against the live tracker.
2. A model may appear in more than one category if it has multiple issues. Total issue counts will therefore exceed the unique model count.
3. Duplicate Model ID rows are counted using distinct Model ID logic — confirm COUNTIF formulas use the deduplication approach from the FormulasHelp tab.
4. OGM Plan Review cutoff: 07/01/2025. QC Release cutoff: 10/01/2025. LSV requires only OGM Plan Review — no QC or Risk Tier.

## Category Analysis
CATEGORY-BY-CATEGORY ANALYSIS
2.1 No Validation in Period (Q1-2025 to Q1-2026)
Priority | CRITICAL | Count | 35 | Definition
Models with no FSV, AR, or LSV activity recorded between Q1-2025 and Q1-2026. The last validation event pre-dates the reporting window.
Sub-Category | Est. Count | Evidence from Comments
Last validation pre-dates Q1-2025 (AR/FSV in 2024) | ~20 | Last AR: 04/22/24, 09/30/24, 08/26/24 etc.
Never validated (no initial FSV) | ~8 | 'No initial FSV has been done'
LSV done but OGM Plan = No | ~7 | LSV date present, OGM Review = No
Recommended Analysis Steps
1. Filter tracker to Category = 'No Validation has been'. Review the Last Validation Date column.
2. Sub-group by: (a) date before Q1-2025, (b) never validated, (c) LSV with OGM = No.
3. For in-use models: flag for urgent scheduling. For retired models: close in tracker.
4. For never-validated models: determine if new (schedule FSV) or legacy (grandfathered).
2.2 AR Available — OGM Plan Not Available (post-07/01/2025)
Priority | HIGH | Count | 61 | Definition
An Annual Review (AR) was completed on or after 07/01/2025, making OGM Plan Review mandatory. However, the OGM Plan column is blank or 'Not Available'.
Step | Action | Detail
1 | Filter by category | Category = 'AR is available, OGM not available after 07/01/2025'
2 | Confirm AR date | Verify AR Date >= 07/01/2025 — not a data-entry error
3 | Check workpapers | OGM Plan may exist in AV document but not recorded in tracker
4 | If truly missing | Escalate to model owner; raise formal exception if needed
5 | Document resolution | Update Comments column; move Category to 'All required assessments completed'
2.3 QC Not Available / Wrong Format (post-10/01/2025)
Priority | HIGH | Count | 39 + 2 | Definition
For FSV/AR events dated >= 10/01/2025, a QC review is mandatory. 39 models are missing QC evidence; 2 models have QC in the wrong format.
Sub-Type | Count | Resolution
QC evidence missing | 39 | Escalate to validation team — locate evidence or re-perform QC step
QC wrong format / template | 2 | Easier fix — reformat to correct template; no re-performance required
Recommended Analysis Steps
1. Confirm FSV/AR date is genuinely >= 10/01/2025 — double-check dates near the cutoff.
2. Check whether QC was completed in SNOW Validation task vs a separate document.
3. For missing QC: escalate to QC Lead (Adam/Bobby) to locate evidence or re-perform.
2.4 'Other' Category — Detailed Sub-Issue Breakdown
Priority | MEDIUM | Count | 91 | Definition
The 'Other' category contains multiple distinct sub-issues that must be split for meaningful analysis and client reporting.
Sub-Issue | ~Count | Evidence / Action
Retired / Re-Designated / Cancelled / Not in Use | 91 | Formally close in tracker; communicate to client
Exception raised — model on track for development | ~5 | Confirm exception ref and development schedule
FSV/AR closed with 'unable to validate' rating | ~4 | Review rating basis; determine if re-validation required
OGM Plan in AV but flagged incorrectly (pre-07/01/25) | ~6 | Verify AR date; correct tracker flag if pre-cutoff
AV document / Report not available on SNOW | ~3 | Escalate to SNOW Admin to locate or re-upload
Reference to email thread (RE: AB1233) | ~3 | Trace thread; ensure findings captured in tracker
FSV does not contain OGM plan assessment | ~7 | Obtain OGM assessment or raise exception
LSV done but OGM not available after cutoff | ~5 | Complete OGM Plan Review or raise exception
QC performed before 10/01/2025 — marked '-' | ~4 | No action required; verify the marker is correct
Recommended Analysis Steps
1. Add helper column 'Other Sub-Type' in your tracker.
2. Use IF/SEARCH formulas to auto-tag each row (see Formulas & Steps sheet).
3. Create a pivot table on 'Other Sub-Type' to count each sub-issue.
4. Replace the single 'Other: 91' in your dashboard with the broken-out sub-counts.

## Action Plan
RECOMMENDED ACTION PLAN
Ref | Action Required | Applicable To | Priority | Owner | Status
A1 | Triage all 35 'No Validation' models — confirm active/retired status | No Validation (35 models) | Critical | Model Risk / Validation Team | Open
A2 | Schedule FSV/AR for all In Use models with no validation in period | No Validation → In Use | Critical | Model Owners | Open
A3 | Formally retire/close models tagged 'No Validation' that are Retired | No Validation → Retired | High | Tracker Owner | Open
A4 | Obtain OGM Plan for 61 AR models missing it (post-07/01/2025) | AR + OGM Missing (61) | High | Validation Team | Open
A5 | Locate or re-perform QC for 39 models missing QC post-10/01/2025 | QC Missing (39) | High | QC Lead / Adam & Bobby | Open
A6 | Reformat QC documents for 2 models with wrong QC format | QC Wrong Format (2) | Medium | Validation Team | Open
A7 | Close out Retired/Cancelled models — update tracker status | Other: Retired 91 models | Medium | Tracker Owner | Open
A8 | Resolve 'Exception Raised' models — confirm development schedule | Other: Exceptions (~5) | Medium | Model Development Team | Open
A9 | Locate AV documents missing from SNOW (~3 models) | Other: Missing on SNOW | Medium | SNOW Admin / Validation Team | Open
A10 | Break 'Other' into sub-categories in tracker for cleaner reporting | All 'Other' models | Low | Tracker Owner | Open
A11 | Add 'Sub-Category' and 'Days Since Last Val' helper columns to tracker | Tracker Enhancement | Low | Tracker Owner | Open

## Formulas & Steps
HOW TO BUILD THE ANALYSIS IN YOUR TRACKER
STEP 1 — Add a 'Sub-Category' Helper Column
In your tracker, add a column after 'Comments'. Label it 'Sub-Category'. Use the formula below (adjust column letters to match your layout).
STEP 2 — Create a Pivot Table on 'No Validation' Rows
Filter Category = 'No Validation has been'. Insert Pivot Table. Drag 'Last Validation Date' to Rows, 'Model ID' to Values (Count). Group dates by Year. Add 'Use Status' to Filters.
STEP 3 — Analyse 'Other' Category Using Comments Keywords
Add a second helper column 'Other Sub-Type'. Use SEARCH() on Comments to auto-tag sub-issues. Then pivot on 'Other Sub-Type' to count each sub-issue.
STEP 4 — Build a 'No Validation Detail' Tab
Create a new sheet 'NoVal_Detail'. Copy-paste only the 'No Validation' rows. Add: Last Val Date, Days Since Last Val, Sub-Type, Use Status, Model Owner, Next Scheduled Val. Sort by Days Since Last Val (desc).
CLIENT REPORT STRUCTURE
Report Section | Length | Content | Notes
Layer 1 — Executive Summary | 1 page | Dashboard KPI cards + top 3 findings + % completion | Lead with this in client meetings
Layer 2 — Category Analysis | 2–3 pages | One section per issue category with counts, sub-breakdown, and root cause | Use the Category Analysis sheet
Layer 3 — Action Register | 1 page | Action table A1–A11 with owner and target date columns | Use the Action Plan sheet
Appendix — Model Lists | As needed | Full list of model IDs per category (filter from tracker and paste) | Clients always ask what 'Other' means — show the breakdown